## Module Tracker
ACOB LIGHTING TECHNOLOGY LIMITED — ERP System Module Development Tracker
Tracks all portal & admin routes — status, descriptions, and delivery timelines
| Completed | In Progress | Not Started
# | Section | Page / Route Title | URL Path | Location | Status | Description / Remark | Timeline
USER PORTAL
1 | USER PORTAL | Profile / Home | /profile | User | Completed | Employee personal dashboard — shows profile info, department, role, recent activity, and quick links to key modules. | Done
2 | USER PORTAL | Notifications | /notifications | User | Completed | Employee notification centre — inbox for system alerts, task assignments, leave decisions, meeting reminders, and broadcasts. | Done
3 | USER PORTAL | Notification Settings | /notifications/settings | Sub-page | Completed | Allows employees to configure notification preferences — choose which event types trigger alerts. | Done
4 | USER PORTAL | Job Description | /job-description | User | Completed | Displays the employee assigned job description with duties, responsibilities, and required competencies. | Done
5 | USER PORTAL | Projects | /projects | Both | In Progress | Employee view of active and past projects — assigned projects, progress, team members, and deadlines. Shared with Admin. | Dependent on Task & KPI completion
6 | USER PORTAL | Tasks | /tasks | Both | In Progress | Personal task board — employees view, filter, and update tasks assigned to them. Shared with Admin. | ~3 weeks
7 | USER PORTAL | Help Desk | /help-desk | Both | Completed | IT & general support ticket system — employees raise tickets for issues or requests. Full status tracking included. | ~2 weeks
8 | USER PORTAL | Reports Hub | /reports | Both | Completed | Employee-facing reports portal — access to weekly meeting reports, KSS documents, minutes of meeting, and action trackers. | Done
9 | USER PORTAL | Weekly Reports | /reports/weekly-reports | Sub-page | Completed | Lists auto-generated departmental weekly reports — employees view and download their department weekly performance summary. | Done
10 | USER PORTAL | Knowledge Sharing Session | /reports/kss | Sub-page | Completed | Knowledge Sharing Session documents portal — view and download KSS presentations uploaded per meeting week. | Done
11 | USER PORTAL | Minutes of Meeting | /reports/minutes-of-meeting | Sub-page | Completed | Access to uploaded Minutes of Meeting PDF documents — filterable by week and year. | Done
12 | USER PORTAL | Action Tracker | /reports/action-tracker | Sub-page | Completed | Employee-facing action tracker — displays open, in-progress, and closed action items from general meetings. | Done
13 | USER PORTAL | Assets | /assets | Both | Completed | Employee view of company assets — lists assets assigned to the individual or their department with status and acquisition details. | Done
14 | USER PORTAL | Payments | /payments | User | Completed | Employee payments ledger — displays salary, allowances, and reimbursement records with status (due/paid/overdue). | Done
15 | USER PORTAL | Documentation | /documentation | Both | Completed | Employee document library — browse company policies, SOPs, and internal documents. Shared with Admin. | Done
16 | USER PORTAL | Department Documents | /documentation/department-documents | Sub-page | In Progress | Department-specific document repository — filtered view of documents belonging to the employee department. | ~1 week
17 | USER PORTAL | Internal Documents | /documentation/internal | Sub-page | Completed | Internal company documents — company-wide policies, HR circulars, compliance documents, and announcements. | Done
18 | USER PORTAL | Feedback | /feedback | Both | Completed | Anonymous or named feedback submission — employees submit suggestions, concerns, or recognition. Shared with Admin. | Done
19 | USER PORTAL | Tools Hub | /tools | Both | Completed | Self-service tool portal — signature generator, watermark tool, and reference letter generator. Shared with Admin. | Done
20 | USER PORTAL | Email Signature Generator | /tools/signature | Sub-page | Completed | Generates a branded ACOB Lighting HTML email signature using the employee profile data — copyable for Outlook or Gmail. | Done
21 | USER PORTAL | Document Watermark Tool | /tools/watermark | Sub-page | Completed | Applies a configurable watermark (confidential, draft, copy, etc.) to uploaded PDF documents with downloadable output. | Done
22 | USER PORTAL | Reference Letter Generator | /tools/reference-generator | Sub-page | In Progress | Generates professional reference letters on company letterhead — customisable recipient and content fields. | ~2 weeks
23 | USER PORTAL | Job Description Tool | /tools/job-description | Sub-page | Completed | Tool for generating or previewing a formatted job description document for recruitment or role clarity purposes. | Done
24 | USER PORTAL | Leave | /leave | User | Completed | Employee leave management — view leave balance, apply for leave, track approval status, and view leave history. | Done
25 | USER PORTAL | Leave Request | /leave/request | Sub-page | In Progress | Leave application form — employee selects leave type, date range, and provides justification. Triggers approval workflow. | ~3 weeks
26 | USER PORTAL | Attendance | /attendance | User | In Progress | Employee attendance dashboard — view clock-in/clock-out records, total hours, and attendance status by date. | TBD
27 | USER PORTAL | Attendance Records | /attendance/records | Sub-page | In Progress | Detailed historical attendance records — filterable by date range with export capability. | TBD
28 | USER PORTAL | Fleet | /fleet | User | In Progress | Company fleet management for employees — view assigned or available vehicles, booking requests, and usage history. | ~2 weeks
29 | USER PORTAL | Goals (PMS) | /goals | User | In Progress | Personal goal setting and tracking — employees set, update, and submit goals for approval with target values and due dates. | TBD
30 | USER PORTAL | Reviews / Performance | /reviews | User | In Progress | Employee performance reviews — view submitted appraisals, ratings, strengths, improvement areas, and goals achieved. | TBD
ADMIN PANEL
31 | ADMIN PANEL | Admin Dashboard | /admin | Admin | Completed | Top-level admin overview — summary stats, quick links to all management modules, and system health indicators. | Done
32 | ADMIN PANEL | HR Management Hub | /admin/hr | Admin | Completed | Central HR administration panel — overview of employees, pending leaves, departments, attendance, and performance KPIs. | Done
33 | ADMIN PANEL | HR – Employees List | /admin/hr/employees | Sub-page | Completed | Full employee directory with filtering by department, status, and role — admin can view, edit, or deactivate profiles. | Done
34 | ADMIN PANEL | HR – Offboarding Conflicts | /admin/hr/employees/offboarding-conflicts | Sub-page | Completed | Flags employees with unresolved offboarding conflicts — e.g. pending leaves, open tickets, or incomplete handovers. | Done
35 | ADMIN PANEL | HR – Departments | /admin/hr/departments | Sub-page | Completed | Department management — create, edit, and manage company departments; view headcount and department hierarchy. | Done
36 | ADMIN PANEL | HR – Leave Approval | /admin/hr/leave/approve | Sub-page | Completed | HR leave approval queue — review pending leave requests, approve or reject with comments, and manage calendar conflicts. | Done
37 | ADMIN PANEL | HR – Fleet Management | /admin/hr/fleet | Sub-page | In Progress | Admin fleet management — register vehicles, assign drivers, manage bookings, and track vehicle maintenance records. | ~3 weeks
38 | ADMIN PANEL | HR – Performance Create | /admin/hr/performance/create | Sub-page | In Progress | Admin tool to initiate a new performance review cycle — set parameters, select employees, define evaluation criteria. | TBD
39 | ADMIN PANEL | HR – Office Location | /admin/hr/office-location | Sub-page | Completed | Manage registered office locations — define geo-fence boundaries for attendance clock-in validation. | Done
40 | ADMIN PANEL | HR – Attendance Reports | /admin/hr/attendance/reports | Sub-page | In Progress | Admin attendance analytics — aggregated attendance data by department, employee, or date range with export options. | TBD
41 | ADMIN PANEL | Finance Hub | /admin/finance | Admin | Completed | Finance overview dashboard — summary of invoices, bills, payments, and financial health indicators across all departments. | Done
42 | ADMIN PANEL | Finance – Invoices | /admin/finance/invoices | Sub-page | Completed | Invoice management — create, view, and track outgoing invoices; status tracking from draft to paid. | Done
43 | ADMIN PANEL | Finance – Payments | /admin/finance/payments | Sub-page | Completed | Admin payments ledger — manage all employee or vendor payment records; filter by status, department, or date. | Done
44 | ADMIN PANEL | Finance – Payments by Dept | /admin/finance/payments/departments | Sub-page | Completed | Department-level payment breakdown — view total payment obligations and disbursements grouped by department. | Done
45 | ADMIN PANEL | Finance – Reports | /admin/finance/reports | Sub-page | Completed | Financial reporting module — generates summary and detailed financial reports exportable to PDF or spreadsheet. | Done
46 | ADMIN PANEL | Projects (Admin) | /admin/projects | Both | In Progress | Admin-side project management — overview of all company projects, team assignment, and progress monitoring. | Dependent on Task completion
47 | ADMIN PANEL | Tasks (Admin) | /admin/tasks | Both | In Progress | Admin task management — view and manage all tasks across all employees and departments; reassign and escalate. | ~4 weeks
48 | ADMIN PANEL | Help Desk (Admin) | /admin/help-desk | Both | In Progress | Admin support ticket management — full queue of all raised tickets, assignment to staff, status updates, and SLA tracking. | ~2 weeks
49 | ADMIN PANEL | Reports Admin Hub | /admin/reports | Both | Completed | Admin reports management centre — upload, manage, and broadcast meeting reports, KSS, minutes, and action points. | Done
50 | ADMIN PANEL | Reports – Weekly Reports | /admin/reports/weekly-reports | Sub-page | Completed | Admin-side weekly report management — view all departmental weekly reports, filter by week/year, and export. | Done
51 | ADMIN PANEL | Reports – KSS Upload | /admin/reports/kss | Sub-page | Completed | Upload and manage Knowledge Sharing Session files — version control, presenter tagging, and per-week tracking. | Done
52 | ADMIN PANEL | Reports – Minutes Upload | /admin/reports/minutes-of-meeting | Sub-page | Completed | Upload and manage Minutes of Meeting PDF documents — versioned per meeting week with current-version tracking. | Done
53 | ADMIN PANEL | Reports – Action Tracker | /admin/reports/action-tracker | Sub-page | Completed | Admin action tracker management — create, update, and close action items; assign responsible parties and deadlines. | Done
54 | ADMIN PANEL | Reports – Meeting Documents | /admin/reports/meeting-documents | Sub-page | Completed | Master view of all meeting documents per week — KSS, minutes, and action point files with download and version info. | Done
55 | ADMIN PANEL | Reports – Weekly Summary Mail | /admin/reports/mail | Sub-page | Completed | Weekly meeting summary broadcast — select recipients, content types (report/KSS/minutes/action tracker), send or schedule emails with PDF attachments. | Done
56 | ADMIN PANEL | Tools (Admin) | /admin/tools | Both | Completed | Admin-accessible utility tools hub — reference generator and other administrative document tools. | Done
57 | ADMIN PANEL | Tools – Reference Generator | /admin/tools/reference-generator | Sub-page | In Progress | Admin reference/introduction letter generator — create and download official company letters on ACOB letterhead. | ~2 weeks
58 | ADMIN PANEL | Notifications (Admin) | /admin/notifications | Both | Completed | Admin notification management centre — send broadcasts, manage meeting notifications, and configure reminder rules. | Done
59 | ADMIN PANEL | Notifications – Broadcast | /admin/notifications/broadcast | Sub-page | Completed | Push broadcast notifications to selected employees or all staff — supports department or role-based targeting. | Done
60 | ADMIN PANEL | Notifications – Meetings | /admin/notifications/meetings | Sub-page | Completed | Manage meeting-related notifications — configure which employees get notified for upcoming general meetings. | Done
61 | ADMIN PANEL | Notifications – Meeting Mail | /admin/notifications/meetings/mail | Sub-page | Completed | Send meeting invite or follow-up emails to selected recipients — linked to the meeting calendar. | Done
62 | ADMIN PANEL | Notifications – Reminders | /admin/notifications/meetings/reminders | Sub-page | Completed | Configure and send meeting reminder notifications — scheduled X hours/days before the next general meeting. | Done
63 | ADMIN PANEL | Communications | /admin/communications | Admin | Completed | Admin communications hub — manage all outgoing company communications including broadcasts and meeting correspondence. | Done
64 | ADMIN PANEL | Communications – Broadcast | /admin/communications/broadcast | Sub-page | Completed | Email/notification broadcast centre — compose and send company-wide or targeted messages to employees. | Done
65 | ADMIN PANEL | Communications – Meetings | /admin/communications/meetings | Sub-page | Completed | Meeting communications management — view meeting schedule, manage invites, and coordinate meeting correspondence. | Done
66 | ADMIN PANEL | Communications – Meeting Mail | /admin/communications/meetings/mail | Sub-page | Completed | Send meeting-specific emails — compose and dispatch formal meeting invitations and follow-ups. | Done
67 | ADMIN PANEL | Communications – Reminders | /admin/communications/meetings/reminders | Sub-page | Completed | Schedule automated meeting reminder emails — configure timing and recipient list for recurring reminders. | Done
68 | ADMIN PANEL | Assets (Admin) | /admin/assets | Both | Completed | Admin asset management — full company asset register with assignment, status tracking, and maintenance logs. | Done
69 | ADMIN PANEL | Assets – Issue Tracking | /admin/assets/issues | Sub-page | Completed | Track reported asset issues and faults — log damage reports, assign repair tickets, and manage resolution status. | Done
70 | ADMIN PANEL | Documentation (Admin) | /admin/documentation | Both | Completed | Admin document management — upload, categorise, and publish company documents visible to employees. | Done
71 | ADMIN PANEL | Documentation – Dept Docs | /admin/documentation/department-documents | Sub-page | In Progress | Admin management of department-specific documents — upload, version, and control visibility per department. | ~1 week
72 | ADMIN PANEL | Documentation – Internal Docs | /admin/documentation/internal | Sub-page | Completed | Admin management of internal company-wide documents — HR policies, compliance docs, company announcements. | Done
73 | ADMIN PANEL | Feedback (Admin) | /admin/feedback | Both | Completed | Admin feedback inbox — review employee feedback submissions; categorise, respond, and track resolution. | Done
74 | ADMIN PANEL | Audit Logs | /admin/audit-logs | Admin | Completed | System-wide audit trail — logs all admin actions with actor, timestamp, entity type, and metadata. | Done
75 | ADMIN PANEL | Settings | /admin/settings | Admin | Completed | Top-level admin settings hub — manage company config, mail settings, user roles, accounts, and system maintenance. | Done
76 | ADMIN PANEL | Settings – Company | /admin/settings/company | Sub-page | Completed | Company profile settings — update company name, address, contact info, and branding used across the system. | Done
77 | ADMIN PANEL | Settings – Mail | /admin/settings/mail | Sub-page | Completed | Email system configuration — manage mail provider settings, enable/disable automated emails per module, and test delivery. | Done
78 | ADMIN PANEL | Settings – Maintenance | /admin/settings/maintenance | Sub-page | Completed | System maintenance mode toggle and scheduling — take the system offline with a custom user-facing message. | Done
79 | ADMIN PANEL | Settings – Roles & Permissions | /admin/settings/roles | Sub-page | Completed | Role-based access control (RBAC) management — define roles, assign module permissions, and configure access scopes. | Done
80 | ADMIN PANEL | Settings – User Management | /admin/settings/users | Sub-page | Completed | Manage all system user accounts — view, activate/deactivate, reset passwords, and change roles. | Done
81 | ADMIN PANEL | Settings – Invite User | /admin/settings/users/invite | Sub-page | Completed | Send employee onboarding invitations — generates a secure signup link and pre-fills department and role data. | Done
82 | ADMIN PANEL | Inventory Hub | /admin/inventory | Admin | In Progress | Admin inventory management — overview of all products, stock levels, warehouse locations, and movement history. | TBD
83 | ADMIN PANEL | Inventory – Products | /admin/inventory/products | Sub-page | In Progress | Full product catalogue — list, filter, and manage all inventory items with SKU, category, and stock quantity. | TBD
84 | ADMIN PANEL | Inventory – Categories | /admin/inventory/categories | Sub-page | In Progress | Product category management — create and organise inventory categories and sub-categories. | TBD
85 | ADMIN PANEL | Inventory – Warehouses | /admin/inventory/warehouses | Sub-page | In Progress | Warehouse/storage location management — register warehouses, zones, and bin locations for stock tracking. | TBD
86 | ADMIN PANEL | Inventory – Stock Movements | /admin/inventory/movements | Sub-page | In Progress | Stock movement log — tracks all inbound and outbound inventory movements with date, quantity, and reference. | TBD
87 | ADMIN PANEL | Purchasing Hub | /admin/purchasing | Admin | In Progress | Procurement management dashboard — overview of active purchase orders, supplier performance, and pending receipts. | TBD
88 | ADMIN PANEL | Purchasing – Orders | /admin/purchasing/orders | Sub-page | In Progress | Purchase order management — list, filter, and track all purchase orders from creation through to receipt. | TBD
89 | ADMIN PANEL | Purchasing – Suppliers | /admin/purchasing/suppliers | Sub-page | In Progress | Supplier directory — register and manage vendors with contact details, payment terms, and performance ratings. | TBD
90 | ADMIN PANEL | Purchasing – Receipts | /admin/purchasing/receipts | Sub-page | In Progress | Goods receipt management — log and confirm delivery of purchased items against purchase orders. | TBD
91 | ADMIN PANEL | Admin Job Descriptions | /admin/job-descriptions | Admin | Completed | Admin management of company job descriptions — create, edit, assign, and publish JDs for all roles. | Done
DEVELOPER TOOLS
92 | DEVELOPER TOOLS | Dev Dashboard | /admin/dev | Admin (Dev) | Completed | Developer-only section overview — quick links to all diagnostic and monitoring tools. | Done
93 | DEVELOPER TOOLS | Login Logs | /admin/dev/login-logs | Admin (Dev) | Completed | System login activity log — all user sign-in events with timestamp, IP, device, and success/failure status. | Done
94 | DEVELOPER TOOLS | Role Escalations | /admin/dev/role-escalations | Admin (Dev) | Completed | Tracks temporary role escalation events — when users were granted elevated permissions and for how long. | Done
95 | DEVELOPER TOOLS | Security Events | /admin/dev/security-events | Admin (Dev) | Completed | Security incident log — records suspicious actions, failed authentication attempts, and policy violations. | Done
96 | DEVELOPER TOOLS | Tests | /admin/dev/tests | Admin (Dev) | Completed | Built-in integration test runner — execute end-to-end system tests and view test results and diagnostics. | Done
97 | DEVELOPER TOOLS | UI Error Monitor | /admin/dev/ui-errors | Admin (Dev) | Completed | Frontend error tracking — logs client-side JavaScript errors and React boundary exceptions with stack traces. | Done
98 | DEVELOPER TOOLS | Dev Maintenance | /admin/dev/maintenance | Admin (Dev) | Completed | Low-level maintenance tools for developers — database migrations, cache clearing, and system diagnostics. | Done
AUTH PAGES
99 | AUTH PAGES | Login | /auth/login | Auth | Completed | Employee login page — email and password authentication with session management via Supabase Auth. | Done
100 | AUTH PAGES | Sign Up | /auth/sign-up | Auth | Completed | New account registration — used during employee onboarding via invite link. | Done
101 | AUTH PAGES | Sign Up Success | /auth/sign-up-success | Auth | Completed | Post-registration confirmation page — confirms successful account creation and guides employee to next steps. | Done
102 | AUTH PAGES | Forgot Password | /auth/forgot-password | Auth | Completed | Password reset request — employee submits their email to receive a secure password reset link. | Done
103 | AUTH PAGES | Reset Password | /auth/reset-password | Auth | Completed | Password reset form — employee sets a new password using the secure token received via email. | Done
104 | AUTH PAGES | Set Password | /auth/set-password | Auth | Completed | Initial password setup page — used by newly invited employees to set their first password. | Done
105 | AUTH PAGES | Setup Account / Onboarding | /auth/setup-account | Auth | Completed | New employee account setup wizard — collects profile details, department, and preferences during first-time login. | Done
106 | AUTH PAGES | Auth Error Page | /auth/error | Auth | Completed | Auth error boundary page — displayed when authentication fails or tokens are invalid/expired. | Done