## Action Tracker
ACOB LIGHTING TECHNOLOGY LIMITED — Action Tracker (All Departments)
Weekly action items from all general meetings ¦ Grouped by department ¦ Generated 26 March 2026
| Closed | In Progress | Open | Overdue
# | Department | Action Item | Status | Priority | Week | Year | Due Date | Description / Notes
ACCOUNTS (58 items)
1 | Accounts | [TSK-000268] To continue the compilation of our documents for 2025 audit exercise for 1st week march | Open | Medium | 6 | 2026 | - | —
2 | Accounts | [TSK-000269] Follow up with our external auditors on the pending tax audit for Fannay Frank. | Open | Medium | 6 | 2026 | - | —
3 | Accounts | [TSK-000267] To complete the filling of annual returns for ITF & PENCOM | Open | Medium | 6 | 2026 | - | —
4 | Accounts | [TSK-000265] To completion of ACOB Lighting Management Account for Q4 2025 and the consolidated accounts for year ended 31st December 2025-10th | Open | Medium | 6 | 2026 | - | —
5 | Accounts | [TSK-000266] To complete the financial report for Q4 2025 to be submitted to INFRACREDIT. | Open | Medium | 6 | 2026 | - | —
6 | Accounts | [TSK-000244] Remit & file the assessed tax liability for Fannay Frank. | Open | Medium | 7 | 2026 | - | —
7 | Accounts | [TSK-000243] To continue the compilation of our documents for 2025 audit exercise for 1st week march | Open | Medium | 7 | 2026 | - | —
8 | Accounts | [TSK-000242] To complete the filling of annual returns for PENCOM | Open | Medium | 7 | 2026 | - | —
9 | Accounts | [TSK-000241] To complete the financial report for Q4 2025 to be submitted to INFRACREDIT. | Open | Medium | 7 | 2026 | - | —
10 | Accounts | [TSK-000240] Engage with team leads on the 2026 annual budget template | Open | Medium | 7 | 2026 | - | —
11 | Accounts | [TSK-000239] To completion of ACOB Lighting Management Account for Q4 2025 and the consolidated accounts for year ended 31st December 2025 | Open | Medium | 7 | 2026 | - | —
12 | Accounts | [TSK-000248] Interface with the Senior management on all pending statutory obligation | Open | Medium | 7 | 2026 | - | —
13 | Accounts | [TSK-000247] Update all payables and receivables for the week under review | Open | Medium | 7 | 2026 | - | —
14 | Accounts | [TSK-000246] Interfaced with the Admin/HR on payroll computation | Open | Medium | 7 | 2026 | - | —
15 | Accounts | [TSK-000245] Follow up with the external auditors with respect to the pending tax audit for Acob Lighting Technology Ltd | Open | Medium | 7 | 2026 | - | —
16 | Accounts | [TSK-000360] Follow up with the external auditors with respect to the pending tax audit for Acob Lighting Technology Ltd | Open | Medium | 8 | 2026 | - | —
17 | Accounts | [TSK-000364] Continue update of the Account Payable/ Account Receivables on the database. | Open | Medium | 8 | 2026 | - | —
18 | Accounts | [TSK-000363] Initiate bank reconciliation for the month of February 2026 | Open | Medium | 8 | 2026 | - | —
19 | Accounts | [TSK-000362] Re-engage the Senior Management on the registration of ACOB GROUP | Open | Medium | 8 | 2026 | - | —
20 | Accounts | [TSK-000361] Update all payables and receivables for the week under review | Open | Medium | 8 | 2026 | - | —
21 | Accounts | [TSK-000352] Engage the Senior Management on the Nigerian Tax Act 2025 and its VAT implication on renewable energy equipment/ACOB Retail segment. | Open | Medium | 8 | 2026 | - | —
22 | Accounts | [TSK-000353] To completion of ACOB Lighting Management Account for year ended 31st December 2025 | Open | Medium | 8 | 2026 | - | —
23 | Accounts | [TSK-000354] Complete the review on company vehicle insurance status | Open | Medium | 8 | 2026 | - | —
24 | Accounts | [TSK-000355] Continue to engage with team leads on the 2026 annual budget template | Open | Medium | 8 | 2026 | - | —
25 | Accounts | [TSK-000356] To complete the financial report for Q4 2025 to be submitted to INFRACREDIT. | Open | Medium | 8 | 2026 | - | —
26 | Accounts | [TSK-000357] To complete the filling of annual returns for PENCOM | Open | Medium | 8 | 2026 | - | —
27 | Accounts | [TSK-000358] To continue the compilation of our documents for 2025 audit exercise for 1st week march | Open | Medium | 8 | 2026 | - | —
28 | Accounts | [TSK-000359] Remit & file the assessed tax liability for Fanny Frank. | Open | Medium | 8 | 2026 | - | —
29 | Accounts | [TSK-000436] Engage the Senior Management on the Nigerian Tax Act 2025 and its VAT implication on renewable energy equipment/ACOB Retail segment. | Open | Medium | 9 | 2026 | - | —
30 | Accounts | [TSK-000446] Continue update of the Account Payable/ Account Receivables on the database | Open | Medium | 9 | 2026 | - | —
31 | Accounts | [TSK-000445] Continue bank reconciliation for the month of February 2026 | Open | Medium | 9 | 2026 | - | —
32 | Accounts | [TSK-000444] Update all payables and receivables for the week under review | Open | Medium | 9 | 2026 | - | —
33 | Accounts | [TSK-000443] Follow up with the external auditors with respect to the pending tax audit for Acob Lighting Technology Ltd | Open | Medium | 9 | 2026 | - | —
34 | Accounts | [TSK-000437] Engage with the external auditors during their exercise this week | Open | Medium | 9 | 2026 | - | —
35 | Accounts | [TSK-000438] Complete the review on company vehicle insurance status to get feedback and documentation from the Admin dept. | Open | Medium | 9 | 2026 | - | —
36 | Accounts | [TSK-000442] Remit & file the assessed tax liability for Fanny Frank the MD has approved this, however, we are waiting for revalidated Remita invoice to make payment | Open | Medium | 9 | 2026 | - | —
37 | Accounts | [TSK-000441] To complete the filling of annual returns for PENCOM | Open | Medium | 9 | 2026 | - | —
38 | Accounts | [TSK-000440] To complete the financial report for Q4 2025 to be submitted to INFRACREDIT once the audit exercise is over by Thursday. | Open | Medium | 9 | 2026 | - | —
39 | Accounts | [TSK-000439] Continue to engage with team leads on the 2026 annual budget template | Open | Medium | 9 | 2026 | - | —
40 | Accounts | [TSK-000473] Initiate our plant valuation process and engage with the committee this week to assign task | Open | Medium | 10 | 2026 | - | —
41 | Accounts | [TSK-000474] Continue bank reconciliation for Q1 2026 | Open | Medium | 10 | 2026 | - | —
42 | Accounts | [TSK-000475] Continue update of the Account Payable/ Account Receivables on the database. | Open | Medium | 10 | 2026 | - | —
43 | Accounts | [TSK-000468] Engage our insurers to get quotation for company vehicle insurance, the Admin department will lead this exercise | Open | Medium | 10 | 2026 | - | —
44 | Accounts | [TSK-000469] Continue to engage with team leads on the 2026 annual budget template | Open | Medium | 10 | 2026 | - | —
45 | Accounts | [TSK-000470] To complete the financial report for Q4 2025 to be submitted to INFRACREDIT once the audit exercise is over by Thursday. | Open | Medium | 10 | 2026 | - | —
46 | Accounts | [TSK-000471] To complete the filling of annual returns for PENCOM | Open | Medium | 10 | 2026 | - | —
47 | Accounts | [TSK-000467] Engage with the external auditors on their upcoming audit exercise | Open | Medium | 10 | 2026 | - | —
48 | Accounts | [TSK-000466] Actively follow up with the NRS team on the ACOB tax audit | Open | Medium | 10 | 2026 | - | —
49 | Accounts | [TSK-000472] Remit & file the assessed tax liability for Fanny Frank | Open | Medium | 10 | 2026 | - | —
50 | Accounts | [TSK-000529] Close out on the vehicle insurance quotation | Open | Medium | 11 | 2026 | - | —
51 | Accounts | [TSK-000527] To actively engage the committee on mini-grid plant valuation process | Open | Medium | 11 | 2026 | - | —
52 | Accounts | [TSK-000526] Remit & file the assessed tax liability for Fanny Frank | Open | Medium | 11 | 2026 | - | —
53 | Accounts | [TSK-000525] To complete the filling of annual returns for PENCOM | Open | Medium | 11 | 2026 | - | —
54 | Accounts | [TSK-000524] Continue to engage with team leads on the 2026 annual budget template | Open | Medium | 11 | 2026 | - | —
55 | Accounts | [TSK-000523] Engage with the external auditors on their upcoming audit exercise | Open | Medium | 11 | 2026 | - | —
56 | Accounts | [TSK-000522] Actively follow up with the NRS team on the ACOB tax audit | Open | Medium | 11 | 2026 | - | —
57 | Accounts | [TSK-000528] Continue bank reconciliation for Q1 2026 up till March 31 2026 | Open | Medium | 11 | 2026 | - | —
58 | Accounts | [TSK-000530] Complete the documentation process for our investment account | Open | Medium | 11 | 2026 | - | —
ADMIN & HR (60 items)
59 | Admin & HR | [TSK-000017] Round up with the HSE Officer on the HSE training conducted on our 5 MST sites. | Open | Medium | 6 | 2026 | - | —
60 | Admin & HR | [TSK-000138] Finalize Research on the available training opportunities for staff capacity development | Open | Medium | 6 | 2026 | - | —
61 | Admin & HR | [TSK-000137] Finalize the Fleet Management and Employee Wellbeing Framework and Policy | Closed | Medium | 6 | 2026 | - | —
62 | Admin & HR | [TSK-000020] And any other task that come to the department | Open | Medium | 6 | 2026 | - | —
63 | Admin & HR | [TSK-000019] See to the smooth welfare of the office | Open | Medium | 6 | 2026 | - | —
64 | Admin & HR | [TSK-000018] Work on the departmental strategic plan for 2026 | Open | Medium | 6 | 2026 | - | —
65 | Admin & HR | [TSK-000257] Fleet management and ensuring BP checks is done by all staff. | Open | Medium | 7 | 2026 | - | —
66 | Admin & HR | [TSK-000258] Follow-up on the SIWES Industrial Training application. | Open | Medium | 7 | 2026 | - | —
67 | Admin & HR | [TSK-000250] A formal request was issued to all leads for the submission of existing policy documents signed by the CEO. We intend to develop policy repository for ACOB. | Open | Medium | 7 | 2026 | - | —
68 | Admin & HR | [TSK-000249] We will commence the development of Admin/HR Departmental strategic plan for 2026 in alignment with the organization’s overall goals. | Open | Medium | 7 | 2026 | - | —
69 | Admin & HR | [TSK-000253] We will audit employee records to identify and address missing or outstanding documentation. | Open | Medium | 7 | 2026 | - | —
70 | Admin & HR | [TSK-000252] The department will conduct a proper inventory and documentation of all bid-related documents to ensure accountability and easy retrieval. | Open | Medium | 7 | 2026 | - | —
71 | Admin & HR | [TSK-000251] A review and restructuring of our filing system will be carried out to ensure proper documentation, accessibility, and compliance. | Open | Medium | 7 | 2026 | - | —
72 | Admin & HR | [TSK-000254] Work will commence on organizing and strengthening the employee performance evaluation process. | Open | Medium | 7 | 2026 | - | —
73 | Admin & HR | [TSK-000255] Payroll management for salaries of staff. | Open | Medium | 7 | 2026 | - | —
74 | Admin & HR | [TSK-000256] Purchase of items as directed by management. | Open | Medium | 7 | 2026 | - | —
75 | Admin & HR | [TSK-000334] Follow up with HCS on the identified gaps in the AXA Mansard Silver Plan and present a summary for decision-making. | Open | Medium | 8 | 2026 | - | —
76 | Admin & HR | [TSK-000347] ⁠Attend to any emerging issues requiring administrative or HR intervention to ensure the smooth and uninterrupted running of the organization. | Open | Medium | 8 | 2026 | - | —
77 | Admin & HR | [TSK-000346] ⁠Continue strengthening the employee performance evaluation process. | Open | Medium | 8 | 2026 | - | —
78 | Admin & HR | [TSK-000345] ⁠Continue strategic plan development for HR/Admin department. | Open | Medium | 8 | 2026 | - | —
79 | Admin & HR | [TSK-000344] Participate in management strategy sessions focused on organizational re-engineering and process improvement. | Open | Medium | 8 | 2026 | - | —
80 | Admin & HR | [TSK-000343] ⁠Fill identified personnel vacancies across departments, including coordination of recruitment and onboarding processes. | Open | Medium | 8 | 2026 | - | —
81 | Admin & HR | [TSK-000342] ⁠Review feedback from the Climate and Carbon Intelligence Training circulation and compile a list of interested staff. | Open | Medium | 8 | 2026 | - | —
82 | Admin & HR | [TSK-000341] ⁠Coordinate fleet movements and ensure smooth vehicle usage to improve efficiency. | Open | Medium | 8 | 2026 | - | —
83 | Admin & HR | [TSK-000340] ⁠Continue follow-up with the SIWES applicant or recommend alternative actions if unresponsive. | Open | Medium | 8 | 2026 | - | —
84 | Admin & HR | [TSK-000339] ⁠Monitor and manage staff payroll-related issues, including resolving any discrepancies arising from the last payroll run. | Open | Medium | 8 | 2026 | - | —
85 | Admin & HR | [TSK-000338] ⁠Ensure staff compliance with BP checks directive. | Open | Medium | 8 | 2026 | - | —
86 | Admin & HR | [TSK-000337] ⁠Finalize and submit the 2026 Admin and HR Budget for Management review and approval. | Open | Medium | 8 | 2026 | - | —
87 | Admin & HR | [TSK-000336] ⁠Commence policy repository process with the complied policy documents received. | Open | Medium | 8 | 2026 | - | —
88 | Admin & HR | [TSK-000335] ⁠Implement corrective actions from the filing system review, including restructuring, proper labeling, and standardization of records. | Open | Medium | 8 | 2026 | - | —
89 | Admin & HR | [TSK-000423] Follow up and finalize on the partnership letter sent to MRS Filling Station and document responses if received. | Open | Medium | 9 | 2026 | - | —
90 | Admin & HR | [TSK-000422] See to the repair of the BP monitoring device to enable continuation of staff health checks. | Open | Medium | 9 | 2026 | - | —
91 | Admin & HR | [TSK-000421] Ensure weekly lunch arrangements for staff and security personnel are properly coordinated with the vendor. | Open | Medium | 9 | 2026 | - | —
92 | Admin & HR | [TSK-000420] Continue planning and coordination for the monthly staff bonding event, including logistics and engagement activities. | Open | Medium | 9 | 2026 | - | —
93 | Admin & HR | [TSK-000419] Oversee fleet management activities and ensure proper maintenance scheduling where required. | Open | Medium | 9 | 2026 | - | —
94 | Admin & HR | [TSK-000418] Continue and finalize the recruitment process, including follow-up with shortlisted candidates and documentation for identified vacancies. | Open | Medium | 9 | 2026 | - | —
95 | Admin & HR | [TSK-000417] Begin review and subsequent implementation and circulation of the compiled policy repository. | Open | Medium | 9 | 2026 | - | —
96 | Admin & HR | [TSK-000416] Continue implementation of the corrective actions from the filing system review, ensuring proper labeling, categorization, and standardization of records. | Open | Medium | 9 | 2026 | - | —
97 | Admin & HR | [TSK-000415] Review and refine the Admin/HR departmental KPIs based on management input. | Open | Medium | 9 | 2026 | - | —
98 | Admin & HR | [TSK-000414] Finalize and submit the 2026 Admin and HR budget for management review and feedback. | Open | Medium | 9 | 2026 | - | —
99 | Admin & HR | [TSK-000424] Prepare and circulate the minutes of meetings and action points from management or departmental meetings during the week. | Open | Medium | 9 | 2026 | - | —
100 | Admin & HR | [TSK-000425] Attend to any emerging administrative and HR matters to ensure smooth organizational operations. | Open | Medium | 9 | 2026 | - | —
101 | Admin & HR | [TSK-000458] Attend to emerging administrative and HR matters to ensure the smooth and uninterrupted running of the organization. | Open | Medium | 10 | 2026 | - | —
102 | Admin & HR | [TSK-000451] Complete the development of the Quarterly Staff Performance Appraisal System and prepare for its rollout to enhance performance management and feedback mechanisms. | Open | Medium | 10 | 2026 | - | —
103 | Admin & HR | [TSK-000452] Strengthen personnel records management by ensuring outstanding staff documentation is submitted and properly integrated into the filing system in line with compliance standards. | Open | Medium | 10 | 2026 | - | —
104 | Admin & HR | [TSK-000453] Advance staff capacity development initiatives by identifying and nominating staff for relevant training opportunities, including the Africa Climate Academy programme. | Open | Medium | 10 | 2026 | - | —
105 | Admin & HR | [TSK-000454] Coordinate staff welfare and wellbeing initiatives, including weekly lunch arrangements for staff and security personnel, and initiate plans for the upcoming monthly staff bonding event to promote team cohesion and morale. | Open | Medium | 10 | 2026 | - | —
106 | Admin & HR | [TSK-000455] Oversee fleet management activities to ensure proper utilization, maintenance coordination, and operational efficiency of company vehicles. | Open | Medium | 10 | 2026 | - | —
107 | Admin & HR | [TSK-000456] Provide ongoing administrative and HR support to Management, including monitoring the implementation of action points from recent meetings and supporting operational efficiency across administrative processes. | Open | Medium | 10 | 2026 | - | —
108 | Admin & HR | [TSK-000457] See to the successful onboarding of new staff into ACOB'S system. | Open | Medium | 10 | 2026 | - | —
109 | Admin & HR | [TSK-000545] Develop a standardized reporting template to enhance consistency and quality of reports. | Open | Medium | 11 | 2026 | - | —
110 | Admin & HR | [TSK-000554] Address emerging administrative and HR matters to ensure the smooth and uninterrupted running of the organization | Open | Medium | 11 | 2026 | - | —
111 | Admin & HR | [TSK-000553] Plan and execute the monthly staff bonding event to promote team cohesion and engagement. | Open | Medium | 11 | 2026 | - | —
112 | Admin & HR | [TSK-000552] Ensure the full consolidation and proper documentation of personnel records in line with compliance standards. | Open | Medium | 11 | 2026 | - | —
113 | Admin & HR | [TSK-000551] Development of the Quarterly Staff Performance Appraisal System in consultation with the HCS. | Open | Medium | 11 | 2026 | - | —
114 | Admin & HR | [TSK-000550] Drive recruitment efforts to fill identified personnel gaps across departments. | Open | Medium | 11 | 2026 | - | —
115 | Admin & HR | [TSK-000548] Finalize the departmental budget in collaboration with the Accounts Department. | Open | Medium | 11 | 2026 | - | —
116 | Admin & HR | [TSK-000549] Oversee payroll administration to ensure accuracy and timely disbursement of staff salaries. | Open | Medium | 11 | 2026 | - | —
117 | Admin & HR | [TSK-000547] Ensure optimal power utilization at the Headquarters by enforcing compliance with existing power management arrangements. | Open | Medium | 11 | 2026 | - | —
118 | Admin & HR | [TSK-000546] Expand fleet management oversight to site vehicles by establishing a comprehensive framework covering maintenance, repair costs, vehicle tracking, and related issues. | Open | Medium | 11 | 2026 | - | —
BUSINESS, GROWTH AND INNOVATION (36 items)
119 | Business, Growth and Innovation | [TSK-000261] COURTESY VISITS TO FMIST AND ICEED. | Open | Medium | 6 | 2026 | - | —
120 | Business, Growth and Innovation | [TSK-000260] INTRODUCE OUR SERVICES TO PROSPECTIVE BUSINESSES TO EXPLORE OPPORTUNITIES. | Open | Medium | 6 | 2026 | - | —
121 | Business, Growth and Innovation | [TSK-000259] FINANLIZE AND SUBMIT GIZ BID. | Open | Medium | 6 | 2026 | - | —
122 | Business, Growth and Innovation | [TSK-000264] ATTEND TO ANY OTHER MATTERS REQUIRING THE DEPARTMENT’S ATTENTION. | Open | Medium | 6 | 2026 | - | —
123 | Business, Growth and Innovation | [TSK-000263] CONTINUE MONITORING AND SOURCING PROJECTS WITHIN THE COMPANY’S PURVIEW. | Open | Medium | 6 | 2026 | - | —
124 | Business, Growth and Innovation | [TSK-000262] FINALIZE THE GROWATT FYLERS WITH IT/COMMUNICATION DEPT. | Open | Medium | 6 | 2026 | - | —
125 | Business, Growth and Innovation | [TSK-000290] ATTEND THE FINANCIAL FACILITY LAUNCH FOR REA & LOTUS BANK | Open | Medium | 7 | 2026 | - | —
126 | Business, Growth and Innovation | [TSK-000292] CONTINUE MONITORING AND SOURCING PROJECTS WITHIN THE COMPANY’S PURVIEW. | Open | Medium | 7 | 2026 | - | —
127 | Business, Growth and Innovation | [TSK-000293] ATTEND TO ANY OTHER MATTERS REQUIRING THE DEPARTMENT’S ATTENTION. | Open | Medium | 7 | 2026 | - | —
128 | Business, Growth and Innovation | [TSK-000288] SUBMIT ALIMA BID. | Open | Medium | 7 | 2026 | - | —
129 | Business, Growth and Innovation | [TSK-000289] COURSTESY VISITS & INTRODUCE OUR SERVICES TO PROSPECTIVE BUSINESSES TO EXPLORE OPPORTUNITIES. | Open | Medium | 7 | 2026 | - | —
130 | Business, Growth and Innovation | [TSK-000291] REVIEW AND MAKE SUBMISSIONS FOR NEW SORT OUT PROJECTS APPLICATIONS. (PIND, CAMCO, OXFAM) WILL BE WORKING CLOSELY WITH RESPECTIVE TEAM MEMBERS. | Open | Medium | 7 | 2026 | - | —
131 | Business, Growth and Innovation | [TSK-000351] ATTEND TO ANY OTHER MATTERS REQUIRING THE DEPARTMENT’S ATTENTION. | Open | Medium | 8 | 2026 | - | —
132 | Business, Growth and Innovation | [TSK-000349] ATTEND A VIRTUAL MEETING WITH ECOWISE ON CARBON CREDIT EOI | Open | Medium | 8 | 2026 | - | —
133 | Business, Growth and Innovation | [TSK-000348] COURSTESY VISITS & INTRODUCE OUR SERVICES TO PROSPECTIVE BUSINESSES TO EXPLORE OPPORTUNITIES. | Open | Medium | 8 | 2026 | - | —
134 | Business, Growth and Innovation | [TSK-000350] CONTINUE MONITORING AND SOURCING PROJECTS WITHIN THE COMPANY’S PURVIEW. | Open | Medium | 8 | 2026 | - | —
135 | Business, Growth and Innovation | [TSK-000388] DEVELOP NEW STRATEGIES TO ENGAGE WITH PROSPECTIVE BUSINESSES TO EXPLORE OPPORTUNITIES. | Open | Medium | 9 | 2026 | - | —
136 | Business, Growth and Innovation | [TSK-000389] COURTESY VISIT & PICK UP BIDDING DOCUMENTS FOR NATIONAL BLOOD SERVICE AGENCY . | Open | Medium | 9 | 2026 | - | —
137 | Business, Growth and Innovation | [TSK-000390] FINANLIZE ON THE GROWATT SOLAR PRODUCT FINANANCING PROPOSAL. | Open | Medium | 9 | 2026 | - | —
138 | Business, Growth and Innovation | [TSK-000391] REVIEW NEW SEARCHED BIDDING APPLICATIONS ( NORAD) | Open | Medium | 9 | 2026 | - | —
139 | Business, Growth and Innovation | [TSK-000392] WORK CLOSELY WITH THE IT/COMM DEPT TO PROVIDE ALL PENDING TASKS. | Open | Medium | 9 | 2026 | - | —
140 | Business, Growth and Innovation | [TSK-000393] CONTINUE SEARCH FOR BID PROJECTS WITHIN THE COMPANYS PURVIEW. | Open | Medium | 9 | 2026 | - | —
141 | Business, Growth and Innovation | [TSK-000394] ATTEND TO ANY OTHER MATTERS REQUIRING THE DEPARTMENTS ATTENTION. | Open | Medium | 9 | 2026 | - | —
142 | Business, Growth and Innovation | [TSK-000463] WORK CLOSELY WITH THE IT/COMM DEPT TO PROVIDE ALL PENDING TASKS. (MARKETING BROCHURE & FYLERS) | Open | Medium | 10 | 2026 | - | —
143 | Business, Growth and Innovation | [TSK-000459] SCHEDULE A COURTESY VISIT WITH THE DIRECTOR FOR NATIONAL BLOOD SERVICE AGENCY . | Open | Medium | 10 | 2026 | - | —
144 | Business, Growth and Innovation | [TSK-000465] ATTEND TO ANY OTHER MATTERS REQUIRING THE DEPARTMENTS ATTENTION. | Open | Medium | 10 | 2026 | - | —
145 | Business, Growth and Innovation | [TSK-000464] CONTINUE SEARCH FOR BID PROJECTS WITHIN THE COMPANYS PURVIEW. | Open | Medium | 10 | 2026 | - | —
146 | Business, Growth and Innovation | [TSK-000460] SEND THE GROWATT SOLAR PRODUCT FINANANCING PROPOSAL FOR SNR MNGT REVIEW. | Open | Medium | 10 | 2026 | - | —
147 | Business, Growth and Innovation | [TSK-000461] SCHEDULE MEETINGS WITH PROSPECTIVE CLIENTS | Open | Medium | 10 | 2026 | - | —
148 | Business, Growth and Innovation | [TSK-000462] SUBMIT THE IDENTIFIED BUSINESS OPPORTUNITY TO SENIOR MANAGEMENT FOR APPROVAL. | Open | Medium | 10 | 2026 | - | —
149 | Business, Growth and Innovation | [TSK-000516] MAKE THE BID SUBMISSION FOR NATIONAL BLOOD SERVICE AGENCY . | Open | Medium | 11 | 2026 | - | —
150 | Business, Growth and Innovation | [TSK-000521] ATTEND TO ANY OTHER MATTERS REQUIRING THE DEPARTMENTS ATTENTION. | Open | Medium | 11 | 2026 | - | —
151 | Business, Growth and Innovation | [TSK-000517] ATTEND THE FINANCIAL BID OPENING FOR FMIST | Open | Medium | 11 | 2026 | - | —
152 | Business, Growth and Innovation | [TSK-000518] SEND THE GROWATT SOLAR PRODUCT FINANANCING PROPOSAL FOR SNR MNGT REVIEW. | Open | Medium | 11 | 2026 | - | —
153 | Business, Growth and Innovation | [TSK-000519] SCHEDULE MEETINGS WITH PROSPECTIVE CLIENTS | Open | Medium | 11 | 2026 | - | —
154 | Business, Growth and Innovation | [TSK-000520] CONTINUE SEARCH FOR BID PROJECTS WITHIN THE COMPANYS PURVIEW. | Open | Medium | 11 | 2026 | - | —
IT AND COMMUNICATIONS (33 items)
155 | IT and Communications | [TSK-000152] Continue our site media coverage | Open | Medium | 4 | 2026 | - | —
156 | IT and Communications | [TSK-000153] Attend to the IT needs of all staff members | Open | Medium | 4 | 2026 | - | —
157 | IT and Communications | [TSK-000154] Post on all our social media handles | Open | Medium | 4 | 2026 | - | —
158 | IT and Communications | [TSK-000155] Connect the remaining printer to the internet | Closed | Medium | 4 | 2026 | - | —
159 | IT and Communications | [TSK-000295] Fix printer-related issues. | Open | Medium | 6 | 2026 | - | —
160 | IT and Communications | [TSK-000294] Post content on all ACOB social media platforms. | Open | Medium | 6 | 2026 | - | —
161 | IT and Communications | [TSK-000299] Continue the implementation of CRM and ERP systems based on feedback from management. | Open | Medium | 6 | 2026 | - | —
162 | IT and Communications | [TSK-000298] Make UPS purchase for those using desktop. | Open | Medium | 6 | 2026 | - | —
163 | IT and Communications | [TSK-000297] Attend to the IT needs of staff members. | Open | Medium | 6 | 2026 | - | —
164 | IT and Communications | [TSK-000296] Continue site media coverage. | Open | Medium | 6 | 2026 | - | —
165 | IT and Communications | [TSK-000271] Attend to the IT needs of staff members. | Open | Medium | 7 | 2026 | - | —
166 | IT and Communications | [TSK-000274] Continue the implementation of CRM and ERP systems based on feedback from management. | Open | Medium | 7 | 2026 | - | —
167 | IT and Communications | [TSK-000273] Continue improvements on the mailing system | Open | Medium | 7 | 2026 | - | —
168 | IT and Communications | [TSK-000270] Post content on all ACOB social media platforms. | Open | Medium | 7 | 2026 | - | —
169 | IT and Communications | [TSK-000272] Make IT purchases and repairs. | Open | Medium | 7 | 2026 | - | —
170 | IT and Communications | [TSK-000100] Complete the design of satefy signs for project sites | Open | Medium | 8 | 2026 | - | —
171 | IT and Communications | [TSK-000104] Continue the implementation of CRM and ERP systems based on feedback | Closed | Medium | 8 | 2026 | - | —
172 | IT and Communications | [TSK-000101] Animate the growatt system marketing and correction of the growatt system | Open | Medium | 8 | 2026 | - | —
173 | IT and Communications | [TSK-000102] Attend to the IT needs of staff members. | Closed | Medium | 8 | 2026 | - | —
174 | IT and Communications | [TSK-000103] Post content on all ACOB social media platforms. | Closed | Medium | 8 | 2026 | - | —
175 | IT and Communications | [TSK-000105] Make IT purchases and repairs. | In Progress | Medium | 8 | 2026 | - | —
176 | IT and Communications | [TSK-000449] Make IT purchases and repairs. | Open | Medium | 9 | 2026 | - | —
177 | IT and Communications | [TSK-000447] Post content on all ACOB social media platforms. | Open | Medium | 9 | 2026 | - | —
178 | IT and Communications | [TSK-000450] Continue the implementation of CRM and ERP systems based on feedback | Open | Medium | 9 | 2026 | - | —
179 | IT and Communications | [TSK-000448] Attend to the IT needs of staff members. | Open | Medium | 9 | 2026 | - | —
180 | IT and Communications | [TSK-000505] Shoot and edit video with the BGI department | Open | Medium | 10 | 2026 | - | —
181 | IT and Communications | [TSK-000510] Finalize the procurement of the IT gadget required by BGI dept. | Open | Medium | 10 | 2026 | - | —
182 | IT and Communications | [TSK-000511] Post on our social media handles | Open | Medium | 10 | 2026 | - | —
183 | IT and Communications | [TSK-000506] Shoot and edit the 3 documentaries of the 10-year anniversary | Open | Medium | 10 | 2026 | - | —
184 | IT and Communications | [TSK-000507] Design the printable materials for the 10-year anniversary | Open | Medium | 10 | 2026 | - | —
185 | IT and Communications | [TSK-000512] Attend to the IT needs of staff members | Open | Medium | 10 | 2026 | - | —
186 | IT and Communications | [TSK-000509] Continue the implementation of 2FA for staff members | Open | Medium | 10 | 2026 | - | —
187 | IT and Communications | [TSK-000508] Continue the implementation of the ERP and CRM systems based on feedback | Open | Medium | 10 | 2026 | - | —
LEGAL, REGULATORY AND COMPLIANCE (24 items)
188 | Legal, Regulatory and Compliance | [TSK-000304] Liaise with NERC to finalize site registrations initiated last year. | Open | Medium | 6 | 2026 | - | —
189 | Legal, Regulatory and Compliance | [TSK-000303] Continue the drafting of Environmental and Social Management Plan (ESMP) report for the nine (9) sites in Ondo State. | Open | Medium | 6 | 2026 | - | —
190 | Legal, Regulatory and Compliance | [TSK-000302] Carry out registration of newly identified sites in Nasarawa state with the Federal Ministry of Environment. | Open | Medium | 6 | 2026 | - | —
191 | Legal, Regulatory and Compliance | [TSK-000301] Collaborate with Operations to schedule HSE training for other locations. | Open | Medium | 6 | 2026 | - | —
192 | Legal, Regulatory and Compliance | [TSK-000300] Continue the review of HSE documentation to ensure alignment with safety standards. | Open | Medium | 6 | 2026 | - | —
193 | Legal, Regulatory and Compliance | [TSK-000308] Liaise with JEDC on the registration of Jengre site in Plateau state. | Open | Medium | 7 | 2026 | - | —
194 | Legal, Regulatory and Compliance | [TSK-000305] Carry out registration of newly identified sites in Nasarawa state with the Federal Ministry of Environment. | Open | Medium | 7 | 2026 | - | —
195 | Legal, Regulatory and Compliance | [TSK-000306] Continue the drafting of Environmental and Social Management Plan (ESMP) report for the nine (9) sites in Ondo State. Essential documents have been provided to Lawrence (Technical Team lead) and we are awaiting feedback. | Open | Medium | 7 | 2026 | - | —
196 | Legal, Regulatory and Compliance | [TSK-000307] Liaise with NERC to finalize site registrations initiated last year. | Open | Medium | 7 | 2026 | - | —
197 | Legal, Regulatory and Compliance | [TSK-000332] Process medical fitness certificates for the personnels to be deployed for Citibank project. | Open | Medium | 8 | 2026 | - | —
198 | Legal, Regulatory and Compliance | [TSK-000333] Collaborate with accounts department to obtain PCC for ACOB and its subsidiaries. | Open | Medium | 8 | 2026 | - | —
199 | Legal, Regulatory and Compliance | [TSK-000331] Finalize with the technical department for the procurement of safety harness(es). | Open | Medium | 8 | 2026 | - | —
200 | Legal, Regulatory and Compliance | [TSK-000330] Continue investigation on the phase imbalance at the power distribution lines in Musha Community, Nasarawa State. | Open | Medium | 8 | 2026 | - | —
201 | Legal, Regulatory and Compliance | [TSK-000427] Collaborate with accounts department to obtain PCC for ACOB and its subsidiaries. | Open | Medium | 9 | 2026 | - | —
202 | Legal, Regulatory and Compliance | [TSK-000429] Visit the E-waste recycling companies we found in Abuja and Accounts department in charge of Companys inventory will be in copy. | Open | Medium | 9 | 2026 | - | —
203 | Legal, Regulatory and Compliance | [TSK-000428] Visit Federal Ministry of Environment to follow up on project approvals and submit tracking ID to be attached to the new registered site file. | Open | Medium | 9 | 2026 | - | —
204 | Legal, Regulatory and Compliance | [TSK-000426] Finalize with the technical department for the procurement of safety harness(es). | Open | Medium | 9 | 2026 | - | —
205 | Legal, Regulatory and Compliance | [TSK-000484] Investigate the recurrence of phase fault incident at Tunga project site, Nasarawa State. | Open | Medium | 10 | 2026 | - | —
206 | Legal, Regulatory and Compliance | [TSK-000487] Continue follow up with JEDC for Jengre Project site registration. | Open | Medium | 10 | 2026 | - | —
207 | Legal, Regulatory and Compliance | [TSK-000486] Collect EIA certificates for Jengre, Plateau state and ten (10) sites in Kaduna state. | Open | Medium | 10 | 2026 | - | —
208 | Legal, Regulatory and Compliance | [TSK-000485] Travel to Makami project site, Kaduna State for bi-annual HSE training and site inspection. | Open | Medium | 10 | 2026 | - | —
209 | Legal, Regulatory and Compliance | [TSK-000515] Visit E-waste recycling company | Open | Medium | 11 | 2026 | - | —
210 | Legal, Regulatory and Compliance | [TSK-000514] Musha project sites, Nasarawa State, respectively. | Open | Medium | 11 | 2026 | - | —
211 | Legal, Regulatory and Compliance | [TSK-000513] Investigate battery communication cable fault and cable burnt at Kyakale and | Open | Medium | 11 | 2026 | - | —
OPERATIONS (47 items)
212 | Operations | [TSK-000309] Completion of Financial Model for Umaisha IMG, subject to Srn Mgnts directives and conclusion with AEDC. (Work alongside Accounts) | Open | Medium | 6 | 2026 | - | —
213 | Operations | [TSK-000320] Provide feedback to Infracredit on DREEF based on updated portfolio list. | Open | Medium | 6 | 2026 | - | —
214 | Operations | [TSK-000315] Attend to all cross-departmental collaboration as arises. | Open | Medium | 6 | 2026 | - | —
215 | Operations | [TSK-000314] Provide feedback to ATC Nigeria & follow up (Snr Mgnt approval) | Open | Medium | 6 | 2026 | - | —
216 | Operations | [TSK-000319] Provision of over 2 weeks performance report across all Mini-grids sites based on new adopted reporting documentation. | Open | Medium | 6 | 2026 | - | —
217 | Operations | [TSK-000318] Complete Project Development structure as mandated by Srn Mngt. | Open | Medium | 6 | 2026 | - | —
218 | Operations | [TSK-000317] Follow up with Sparkmeter for firmware update of the Grid Monitors | Open | Medium | 6 | 2026 | - | —
219 | Operations | [TSK-000313] Coordinate team for Adebayo new street stringing works, meter replacement etc. | Open | Medium | 6 | 2026 | - | —
220 | Operations | [TSK-000316] Attend to all Operations Concerns & Support all Ongoing deployment works. | Open | Medium | 6 | 2026 | - | —
221 | Operations | [TSK-000312] Continue works on the ongoing sparkmeter configuration in Adebayo. | Open | Medium | 6 | 2026 | - | —
222 | Operations | [TSK-000311] Work on resubmission of DARES PBG application for specific sites. (Subject to Snr Mgnt Instruction) | Open | Medium | 6 | 2026 | - | —
223 | Operations | [TSK-000310] Provide additional documentation to AEDC on Umaisha as requested, subject to Snr Mgnt directives. | Open | Medium | 6 | 2026 | - | —
224 | Operations | [TSK-000281] Advance Adebayo new street stringing works, meter replacement etc. (Subject to Hiab’s arrival to site) | Open | Medium | 7 | 2026 | - | —
225 | Operations | [TSK-000282] Facilitate additional gateway installation across the MST sites. | Open | Medium | 7 | 2026 | - | —
226 | Operations | [TSK-000280] Recommence sparkmeter configuration in Adebayo. (Pending OEM feedback) | Open | Medium | 7 | 2026 | - | —
227 | Operations | [TSK-000279] Conduct in-house departmental review meeting. | Open | Medium | 7 | 2026 | - | —
228 | Operations | [TSK-000278] Resubmission of DARES PBG application for specific sites. (Subject to Snr Mgnt Instruction) | Open | Medium | 7 | 2026 | - | —
229 | Operations | [TSK-000277] Complete Meter re-evaluation and subcontractor sign-off across MST sites. | Open | Medium | 7 | 2026 | - | —
230 | Operations | [TSK-000276] Complete Project Development structure as mandated by Snr Mngt. | Open | Medium | 7 | 2026 | - | —
231 | Operations | [TSK-000275] Work on PIND application alongside BGI as mandated by Snr Mgnt. | Open | Medium | 7 | 2026 | - | —
232 | Operations | [TSK-000287] Follow up with Sparkmeter for firmware update of the Grid Monitors (Pending OEM feedback). | Open | Medium | 7 | 2026 | - | —
233 | Operations | [TSK-000286] Attend to all Operations Concerns & Support all Ongoing deployment works. | Open | Medium | 7 | 2026 | - | —
234 | Operations | [TSK-000285] Attend to all cross-departmental collaboration as arises. | Open | Medium | 7 | 2026 | - | —
235 | Operations | [TSK-000284] Follow-up with ATC Nigeria on Proposed Tariff & Next Steps | Open | Medium | 7 | 2026 | - | —
236 | Operations | [TSK-000283] Facilitate team & material deployment to the AMP site (Subject to Hiab’s arrival to site) | Open | Medium | 7 | 2026 | - | —
237 | Operations | [TSK-000385] Attend to all cross-departmental collaboration as arises. | Open | Medium | 8 | 2026 | - | —
238 | Operations | [TSK-000383] Follow up with Sparkmeter on new batch of meter configuration as agreed. | Open | Medium | 8 | 2026 | - | —
239 | Operations | [TSK-000382] Facilitate repairs of Adebayo Inverters and subsequent return. | Open | Medium | 8 | 2026 | - | —
240 | Operations | [TSK-000381] Have follow up calls with Sparkmeter on Grid Monitor Firmware Update. | Open | Medium | 8 | 2026 | - | —
241 | Operations | [TSK-000386] Attend to all Operations Concerns & Support all Ongoing deployment works. | Open | Medium | 8 | 2026 | - | —
242 | Operations | [TSK-000384] Follow-up with Calin meter on 3phase meter configurations. | Open | Medium | 8 | 2026 | - | —
243 | Operations | [TSK-000387] Follow up with Sparkmeter for firmware update of the Grid Monitors (Pending OEM feedback). | Open | Medium | 8 | 2026 | - | —
244 | Operations | [TSK-000412] Attend to all Operations Concerns & Support all Ongoing deployment works. | Open | Medium | 9 | 2026 | - | —
245 | Operations | [TSK-000407] Have follow up calls with Sparkmeter on Grid Monitor Firmware Update. | Open | Medium | 9 | 2026 | - | —
246 | Operations | [TSK-000408] Facilitate repairs of Adebayo Inverters and subsequent return. | Open | Medium | 9 | 2026 | - | —
247 | Operations | [TSK-000409] Follow up with Sparkmeter on new batch of meter configuration as agreed. | Open | Medium | 9 | 2026 | - | —
248 | Operations | [TSK-000410] Follow-up with Calin meter on 3phase meter configurations. | Open | Medium | 9 | 2026 | - | —
249 | Operations | [TSK-000411] Attend to all cross-departmental collaboration as arises. | Open | Medium | 9 | 2026 | - | —
250 | Operations | [TSK-000413] Follow up with Sparkmeter for firmware update of the Grid Monitors (Pending OEM feedback). | Open | Medium | 9 | 2026 | - | —
251 | Operations | [TSK-000479] Attend to Various Distribution Network faults across various MST sites. | Open | Medium | 10 | 2026 | - | —
252 | Operations | [TSK-000476] Follow up with Sparkmeter on Grid Monitor Firmware Update. | Open | Medium | 10 | 2026 | - | —
253 | Operations | [TSK-000480] Facilitate the Purchase of sim cards for the Calin meter data gateways. | Open | Medium | 10 | 2026 | - | —
254 | Operations | [TSK-000477] Facilitate repairs of Adebayo Inverters and subsequent return. | Open | Medium | 10 | 2026 | - | —
255 | Operations | [TSK-000478] Follow up with Sparkmeter on new batch of meter configuration . | Open | Medium | 10 | 2026 | - | —
256 | Operations | [TSK-000481] Follow up on Conversations with Opay and Ogaranya. | Open | Medium | 10 | 2026 | - | —
257 | Operations | [TSK-000482] Attend to all cross-departmental collaboration as arises. | Open | Medium | 10 | 2026 | - | —
258 | Operations | [TSK-000483] Attend to all Operations Concerns & Support all Ongoing deployment works. | Open | Medium | 10 | 2026 | - | —
PROJECT (49 items)
259 | Project | [TSK-000373] Commence development of Financial Model of ALL ACOB mini-grid portfolio sites as mandated by Snr Mgnt. (Starting with the MST sites to aid NERC submission) | Open | Medium | 8 | 2026 | - | —
260 | Project | [TSK-000378] Follow-up with Larzic on ongoing IMAS Due Dilligence. | Open | Medium | 8 | 2026 | - | —
261 | Project | [TSK-000377] Have follow-up calls with ATC Nigeria on proposed commercial offer. | Open | Medium | 8 | 2026 | - | —
262 | Project | [TSK-000376] Oversee, support & attend to all ongoing project deployment works. | Open | Medium | 8 | 2026 | - | —
263 | Project | [TSK-000375] Join Operations Team on follow-up calls with Sparkmeter on Grid Monitor Firmware Update, & assist in the ongoing meter configurations. | Open | Medium | 8 | 2026 | - | —
264 | Project | [TSK-000374] Commence site scoping and profiling of MESH Grid sites with follow-up conversation with OKRA. | Open | Medium | 8 | 2026 | - | —
265 | Project | [TSK-000372] Review updated actual DARES PBG BOQs as mandated by Snr Mgnt & commence resubmission of site specific application. | Open | Medium | 8 | 2026 | - | —
266 | Project | [TSK-000371] Commence development of work plan and departmental strategy for the Projects Team as mandated by Snr Mgnt. | Open | Medium | 8 | 2026 | - | —
267 | Project | [TSK-000379] Work with R&C to close out on DREEF Joint Development Agreement for ACOB Portfolio. | Open | Medium | 8 | 2026 | - | —
268 | Project | [TSK-000380] Provide updated Financial Model & Follow-up with AEDC on Umaisha. | Open | Medium | 8 | 2026 | - | —
269 | Project | [TSK-000397] Conduct desktop research & profiling of all IMG sites across Nasarawa, Ondo states etc. | Open | Medium | 9 | 2026 | - | —
270 | Project | [TSK-000396] Finalise review updated actual DARES PBG BOQs with Snr Mgnt & commence resubmission of site specific application. | Open | Medium | 9 | 2026 | - | —
271 | Project | [TSK-000406] Provide cross departmental support where necessary. | Open | Medium | 9 | 2026 | - | —
272 | Project | [TSK-000405] Engage Snr Mgnt regarding the DREEF Joint Development Agreement. | Open | Medium | 9 | 2026 | - | —
273 | Project | [TSK-000404] Facilitate EA & MOU renewals across sites that has expired. | Open | Medium | 9 | 2026 | - | —
274 | Project | [TSK-000395] Finalise development of work plan and departmental strategy for the Projects Team for Snr Mgnt reviews | Open | Medium | 9 | 2026 | - | —
275 | Project | [TSK-000403] Facilitate IMAS Material collection & delivery to Nasarawa & Plateau States. | Open | Medium | 9 | 2026 | - | —
276 | Project | [TSK-000402] Oversee, support & attend to all ongoing project deployment works. | Open | Medium | 9 | 2026 | - | —
277 | Project | [TSK-000401] Work alongside Operations Dept. on concluding ongoing Sparkmeter configuration. | Open | Medium | 9 | 2026 | - | —
278 | Project | [TSK-000400] Review Larzic report on Jengre & Work with Technical on providing additional document. | Open | Medium | 9 | 2026 | - | —
279 | Project | [TSK-000399] Update Umaisha TPA & review with R/C alongside HCS to provide response to AEDC. | Open | Medium | 9 | 2026 | - | —
280 | Project | [TSK-000398] Commence development of Financial Model of ALL ACOB mini-grid portfolio sites as mandated by Snr Mgnt. (Starting with the MST sites to aid NERC submission). | Open | Medium | 9 | 2026 | - | —
281 | Project | [TSK-000500] Provide cross departmental support where necessary. | Open | Medium | 10 | 2026 | - | —
282 | Project | [TSK-000499] Oversee, support & attend to all ongoing project deployment works. | Open | Medium | 10 | 2026 | - | —
283 | Project | [TSK-000494] Liaise with R/C & Admin for the development of Sub-contractor onboarding modalities & framework. | Open | Medium | 10 | 2026 | - | —
284 | Project | [TSK-000491] Continue development of Financial Model of ALL ACOB mini-grid portfolio (Atleast 2 sites to be completed this week). | Open | Medium | 10 | 2026 | - | —
285 | Project | [TSK-000492] Work alongside Technical for the development of BOQ, Financial Model & SLDs for DARES PBG IMG portfolio 1 as mandated by Snr Mgnt. | Open | Medium | 10 | 2026 | - | —
286 | Project | [TSK-000497] Complete the ongoing IMAS Material collection & delivery to Nasarawa & Plateau States. | Open | Medium | 10 | 2026 | - | —
287 | Project | [TSK-000496] Work alongside Operations on concluding ongoing Sparkmeter configuration. | Open | Medium | 10 | 2026 | - | —
288 | Project | [TSK-000488] Complete development of work plan and departmental strategy for the Projects Team. Conduct Departmental Strategy Review meeting. | Open | Medium | 10 | 2026 | - | —
289 | Project | [TSK-000495] Complete the development of an in-house Project Deployment Monitoring Dashboard | Open | Medium | 10 | 2026 | - | —
290 | Project | [TSK-000493] Follow-up with R/C on TPA review for onwards submission to AEDC; & POC reviews for feedback to ATC. | Open | Medium | 10 | 2026 | - | —
291 | Project | [TSK-000489] Review completed actual DARES PBG BOQs with Snr Mgnt & commence resubmission of site specific application. | Open | Medium | 10 | 2026 | - | —
292 | Project | [TSK-000490] Continue desktop research & profiling of additional IMG sites across Nigeria | Open | Medium | 10 | 2026 | - | —
293 | Project | [TSK-000498] Facilitate EA & MOU renewals across sites that has expired. | Open | Medium | 10 | 2026 | - | —
294 | Project | [TSK-000532] Facilitate sub-contractor return to sites in Ondo & Nasarawa. | Open | Medium | 11 | 2026 | - | —
295 | Project | [TSK-000544] Provide cross departmental support where necessary. | Open | Medium | 11 | 2026 | - | —
296 | Project | [TSK-000543] Oversee, support & attend to all ongoing project deployment works. | Open | Medium | 11 | 2026 | - | —
297 | Project | [TSK-000542] Facilitate EA & MOU renewals across sites that has expired. | Open | Medium | 11 | 2026 | - | —
298 | Project | [TSK-000541] Complete the ongoing IMAS Material collection & delivery to Nasarawa & Plateau States. | Open | Medium | 11 | 2026 | - | —
299 | Project | [TSK-000540] Work alongside Operations on concluding ongoing Sparkmeter configuration. | Open | Medium | 11 | 2026 | - | —
300 | Project | [TSK-000539] Complete the development of an in-house Project Deployment Monitoring Dashboard | Open | Medium | 11 | 2026 | - | —
301 | Project | [TSK-000538] Liaise with R/C & Admin for the development of Sub-contractor onboarding modalities & framework. | Open | Medium | 11 | 2026 | - | —
302 | Project | [TSK-000537] Follow-up with R/C on TPA review for onwards submission to AEDC; & POC reviews for feedback to ATC. | Open | Medium | 11 | 2026 | - | —
303 | Project | [TSK-000536] Work alongside Technical for the development of BOQ, Financial Model & SLDs for DARES PBG IMG portfolio 1 as mandated by Snr Mgnt. | Open | Medium | 11 | 2026 | - | —
304 | Project | [TSK-000535] Continue development of Financial Model of ALL ACOB mini-grid portfolio (Atleast 2 sites to be completed this week). | Open | Medium | 11 | 2026 | - | —
305 | Project | [TSK-000534] Continue desktop research & profiling of additional IMG sites across Nigeria. | Open | Medium | 11 | 2026 | - | —
306 | Project | [TSK-000533] Complete resubmission of remaining DARES PBG site. | Open | Medium | 11 | 2026 | - | —
307 | Project | [TSK-000531] Conduct In-house Departmental Strategy Review meeting(Review Strategy Document) | Open | Medium | 11 | 2026 | - | —
TECHNICAL (25 items)
308 | Technical | [TSK-000321] Conclude on GIZ bid documentation. | Open | Medium | 6 | 2026 | - | —
309 | Technical | [TSK-000325] Plan for wiring materials at NADDC to commence wiring. | Open | Medium | 6 | 2026 | - | —
310 | Technical | [TSK-000324] Provide technical support to onsite team members | Open | Medium | 6 | 2026 | - | —
311 | Technical | [TSK-000323] Resolve Tunga distribution line fault. | Open | Medium | 6 | 2026 | - | —
312 | Technical | [TSK-000322] Continue electrical works and commence soak away, POP/suspended ceiling, roofing sheet installation and electrical piping at NADDC Imo site. | Open | Medium | 6 | 2026 | - | —
313 | Technical | [TSK-000328] Continue system monitoring, technical supervision, and operational support across all sites. | Open | Medium | 7 | 2026 | - | —
314 | Technical | [TSK-000329] Follow up and provide support to team members at project sites | Open | Medium | 7 | 2026 | - | —
315 | Technical | [TSK-000326] Conclude consultancy frameworks, and technical documentation bids and Citibank projects. | Open | Medium | 7 | 2026 | - | —
316 | Technical | [TSK-000327] Commence electrical wiring and fitting works as well as ceiling and POP works in addition to other works at NADDC | Open | Medium | 7 | 2026 | - | —
317 | Technical | [TSK-000368] Continue electrical wiring, installations and construction activities at NADDC project (Imo), including POP, suspended ceiling, roofing sheets installation, and doors . | Open | Medium | 8 | 2026 | - | —
318 | Technical | [TSK-000367] Commencement of Bondu installation materials delivery. | Open | Medium | 8 | 2026 | - | —
319 | Technical | [TSK-000366] Adebayo pole planting and stringing works. | Open | Medium | 8 | 2026 | - | —
320 | Technical | [TSK-000365] Develop standard BOQ for large-scale solar projects ranging from 100kWp to 5MWp. | Open | Medium | 8 | 2026 | - | —
321 | Technical | [TSK-000370] Provide support to team members across ongoing project sites | Open | Medium | 8 | 2026 | - | —
322 | Technical | [TSK-000369] Attend meeting at AfDB with the project consultant and project owner. | Open | Medium | 8 | 2026 | - | —
323 | Technical | [TSK-000434] Bondu system installation and commissioning | Open | Medium | 9 | 2026 | - | —
324 | Technical | [TSK-000430] Complete the remaining stringing activites for the Adebayo community power extension extension project. | Open | Medium | 9 | 2026 | - | —
325 | Technical | [TSK-000431] Commence installation of electrical fittings at the NADDC project site in Owerri. | Open | Medium | 9 | 2026 | - | —
326 | Technical | [TSK-000435] Maintain technical monitoring and operational oversight of existing systems and ongoing project activities. | Open | Medium | 9 | 2026 | - | —
327 | Technical | [TSK-000432] Continue PV base casting and structural works at the Maraba Udege solar project site. | Open | Medium | 9 | 2026 | - | —
328 | Technical | [TSK-000433] Swapping of Growatt battery system | Open | Medium | 9 | 2026 | - | —
329 | Technical | [TSK-000502] Continue technical designs and PVsyst simulations for new interconnected mini-grid sites. | Open | Medium | 10 | 2026 | - | —
330 | Technical | [TSK-000504] Provide technical support to team members across various project sites. | Open | Medium | 10 | 2026 | - | —
331 | Technical | [TSK-000501] Finalize the remaining PV mounting and connections, electrical fittings, and plumbing installations at the Bondu community and NADDC sites. | Open | Medium | 10 | 2026 | - | —
332 | Technical | [TSK-000503] Coordinate with the Growatt technical team for onsite battery firmware updates and troubleshooting across Infra Credit site. | Open | Medium | 10 | 2026 | - | —
Total: 332 action items ¦ 5 Closed ¦ 1 In Progress ¦ 326 Open ¦ 8 departments